## 版权说明
本模板由Scrum中文网提供，欢迎推荐给任何在实践Scrum的朋友使用。

Scrum中文网(ScrumCN.COM)版权所有

## 产品Backlog
产品Backlog		产品（项目）名称					Sprints
		产品负责人					Total workload	517		1	2	3	4	5	6
				600	400	250	150	0
				totals		0
				600	450
PBI_ID	priority	Backlog type	Functional/nonFunctional	User story (product Backlog entry description)	Acceptance conditions (satisfaction conditions)	the complexity	Sprint	Estimated initial workload_x000D_ / (User story point)	Adjustment coefficient	adjusted_x000D_ / Estimated workload_x000D_ / (User story point)	status
PBI_01	100	new demand		as a student i want to create a new account			sprint1	5	1	5	完成
PBI_02	200	defect		as a site member i want to login			sprint1	3	1	3	完成
PBI_03	300	new demand		as a site member i want to logout			sprint1	5	1	5	完成
PBI_04	400	new demand		As a site visitor, I can read current news on the home page,events selected by the site editor			sprint1	10	1	10	完成
PBI_05	500	new demand		As a site visitor, I can access old news that is no longer on the home page			sprint1	5	1	5	完成
PBI_06	600	new demand		As a site visitor, I can email news items to the editor. (Note: this could just be an email link to / the editor.)			sprint1	15	1	15	完成
PBI_07	700	new demand		as a site visitor, I can view university profiles			sprint1	10	1	10	完成
PBI_08	800	new demand		as a site visitor, I can view interactions comments			sprint1	8	1	8	完成
PBI_09	900	new demand		as a site member I can view other members profiles belonging to my university and those from other universities whose profiles are public			sprint2	15	1	15	完成
PBI_10	1000	new demand		as			sprint2	2	1	5	完成
PBI_11	1100	new demand					sprint2	10	1	10	完成
PBI_12	1200	new demand	功能性					5	1	5	完成
PBI_13	1300	new demand					15	1	15	完成
PBI_14	1400	defect					10	1	10	完成
PBI_15	1500	defect					8	1	8	完成
PBI_16	1600	new demand					15	1	15	完成
PBI_17	1700	new demand					3	1	3	完成
PBI_18	1800	new demand		用户故事示例18用户故事示例18				5	1	5	完成
PBI_19	1900	new demand		用户故事示例19用户故事示例19				10	1	10	完成
PBI_20	2000	new demand		用户故事示例20用户故事示例20				5	1	5	完成
PBI_21	2100	new demand		用户故事示例21用户故事示例21				10	1	10	未开始
PBI_22	2200	new demand		用户故事示例22用户故事示例22				15	1	15	未开始
PBI_23	2300	new demand		用户故事示例23用户故事示例23				20	1	20	未开始
PBI_24	2400	new demand		用户故事示例24用户故事示例24				20	1	20	未开始
PBI_25	2500	new demand		用户故事示例25用户故事示例25				10	1	10	未开始
PBI_26	2600	new demand		用户故事示例26用户故事示例26				10	1	10	未开始
PBI_27	2700	new demand		用户故事示例27				20	1	20	未开始
PBI_28	2800	new demand		用户故事示例28				20	1	20	未开始
PBI_29	2900	new demand		用户故事示例29				10	1	10	未开始
PBI_30	3000	new demand		用户故事示例30				10	1	10	未开始
PBI_31	3100	new demand		用户故事示例31				20	1	20	未开始
PBI_32	3200	new demand		用户故事示例32				20	1	20	未开始
PBI_33	3300	new demand		用户故事示例33				15	1	15	未开始
PBI_34	3400	new demand		用户故事示例34				25	1	25	未开始
PBI_35	3500	new demand		用户故事示例35				15	1	15	未开始
PBI_36	3600	new demand		用户故事示例36				20	1	20	未开始
PBI_37	3700	new demand		用户故事示例37				20	1	20	未开始
PBI_38	3800	new demand		用户故事示例38				15	1	15	未开始
PBI_39	3900	new demand		用户故事示例39				25	1	25	未开始
PBI_40	4000	new demand		用户故事示例40				30	1	30	未开始

## 团队速率
团队1

Sprint 1	Sprint 2	Sprint 3	Sprint 4	Sprint 5
75	80	85	80	90

团队2

Sprint 1	Sprint 2	Sprint 3	Sprint 4	Sprint 5
80	85	75	80	85

## 发布燃尽图
发布燃尽图 / Sprints / 剩余工作量